## Instructions
Your Name: | Isioma Nnodum
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
| 1.5 |  | Tuesday Meeting
| 1.25 |  | Thursday Meeting
| 3 |  | Setting Up the Asana Workspace
| 0.5 |  | Updating resume and uploading it to GDrive
| 4.75 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 1.92 |  | Tuesday Meeting
| 1.92 |  | Thursday Meeting
| 3.84 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 2 |  | 6/17 Agenda
| 1.9167 |  | Tuesday Meeting
| 1.92 |  | Thursday Meeting
| 5.8367 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 1.92 |  | Tuesday Meeting
| 1.92 |  | Thursday Meeting
| 1 |  | 6/24 Agenda
| 4.84 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 2 |  | Monday Meeting
| 2 |  | Tuesday Meeting
| 2 |  | Thursday Meeting
| 6 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 2 |  | Monday Meeting
| 2 |  | Tuesday Meeting
| 2 |  | Thursday Meeting
| 6 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 2 |  | Tuesday Meeting
| 2 |  | Thursday Meeting
| 4 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 2 |  | Preparing Skeleton Project
| 1.5 |  | Monday Meeting
| 2 |  | Tuesday Meeting
| 2 |  | Thursday Meeting
| 5.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 1.5 | EST | Monday Meeting
| 2 |  | Tuesday Meeting
| 3.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 0.5 | 0.5 | Isioma: Identifying the reason Alex's delete request didn't work
| 4.5 | 4.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 4 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 3.8 | 3.8 | Isioma: Refactored project to use latest versions of the core controllers, models and processes Cleaned up states and controllers directories and definitions Added ability to login and and logout of the application Updated application UI to better use bootstrap components Sending update email to team
| 7.8 | 7.8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 2 | Add client facades for backend model apis
|  | 6 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 2.57 | 2 | Added factories module, model factory, endpoint factory, student serv​ice,​ ​and program service. Added student service to create student form and A​​dded parts of program service to the add program controller. Added 404 page. Added data binding to create student form and updated binding in add​ ​program form.​
| 6.57 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Team Meeting
|  | 2 | Built Web demo deployment for paul
|  | 6 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 0.5 | 0.5 | Updated bootstrap buttons and templates to use css grid
Yes | 3 | 3 | Built Web demo deployment for paul
Yes | 2 | 2 | Began writing Wizard Factory and Services. Began integrating with student create controller
Yes | 2 | 2 | Wrapped up initial iteration of wizard factory and service Added ng-grid to bower config
| 11.5 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 3 | Code Improvements
|  | 7 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 3 | 3 | Isioma: - Code improvements - - Improved file uploads - - State transition flow - Deploying application
| 7 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 2 | Add students to class
|  | 2 | Application Installer
|  | 8 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 2.17 | 2 | Adding support for adding students to class. Code Improvements
Yes | 2 | 2 | Started development of installer
| 8.17 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 2 | Application Installer
|  | 6 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 4.5 | 2 | Continued development of application installer - - Improved post installer script - - Looks for mongodb service and installs one if not found - - Added node windows service integration so application can be run as a windows service. - - Updated installer
| 8.5 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 2 | Application Installer
|  | 6 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 4 | 2 | Preparing and testing the installer
Yes | 2 | 2 | Making changes to the installer and updating the live application
| 10 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 2 | Application Installer
|  | 6 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 2 | 2 | Updating the application installer and sending to Paul
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 4 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
| 4 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 2 | Import Students from CSV
|  | 6 | TOTAL TIME
Issues

## 2-Wk11
Second Term - Week 11
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 4 | 2 | Began adding support for importing students from a csv file
| 8 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 2 | Poster Work
|  | 6 | TOTAL TIME
Issues

## 2-Wk12
Second Term - Week 12
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Meeting
Yes | 2 | 2 | Sponsor Meeting
Yes | 5.6 | 2 | Poster Work
Yes | 5.8 | 2.4 | Worked on Import Students from CSV feature Completed Import Students from CSV
Yes | 2.32 | 2.32 | Updates to the application installer
Yes | 2.5 | 2.5 | Fixed issues with the project poster and resubmitted to the printer
| 20.22 | 13.22 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 2 | Development of export students data
|  | 2 | Development of export program data
|  | 2 | export class data
|  | 2 | export workshop data
|  | 1 | export attendance data
|  | 1 | export rank data
|  | 14 | TOTAL TIME
Issues

## 2-Wk13
Second Term - Week 13
Accomplished this week
Done? | ACT | EST | Task
|  | 2 | Team Meeting
|  | 2 | Sponsor Meeting
|  | 2 | Development of export students data
|  | 2 | Development of export program data
|  | 2 | export class data
| 0 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | export workshop data
|  | 1 | export attendance data
|  | 1 | export rank data
|  | 2 | Team meeting
|  | 6 | TOTAL TIME
Issues

## 2-Wk14
Second Term - Week 14
Accomplished this week
Done? | ACT | EST | Task
|  | 2 | export workshop data
|  | 2 | Team meeting
| 0 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Work on technical report
|  | 2 | Complete export features
|  | 5 | TOTAL TIME
Issues

## 2-Wk15
Second Term - Week 15
Accomplished this week
Done? | ACT | EST | Task
|  | 3 | Work on technical report
|  | 2 | Complete export features
| 0 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Work on technical report
|  | 3 | Compile all project files
|  | 6 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
|  | 3 | Work on technical report
|  | 3 | Compile all project files
| 0 | 6 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
4.75 | 0 | 3.84 | 0 | 5.8367 | 0 | 4.84 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 4 | 0 | 5.5 | 0 | 3.5 | 0 | 0
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-11e | t2-11a | t2-12e | t2-12a | t2-13e | t2-13a | t2-14e | t2-14a | t2-15e | t2-15a | t2-fe | t2-fa
4.5 | 4.5 | 7.8 | 7.8 | 6 | 6.57 | 11.5 | 11.5 | 7 | 7 | 8 | 8.17 | 6 | 8.5 | 8 | 10 | 6 | 6 | 4 | 4 | 6 | 8 | 13.22 | 20.22 | 10 | 0 | 4 | 0 | 5 | 0 | 6 | 0