## Instructions
Your Name: | Stefano Sansone
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Yes | 0.5 |  | Attended first class
Yes | 0.5 |  | Discussed expectations of team and team introductions
Yes | 1 |  | Went over the project at a high level
Yes | 1 |  | Met with the project sponsor
| 0.25 |  | Review of synopsis
| 3.25 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Submit a photo and resume
|  | 1.5 | Discuss requirements and feedback from sponsor meeting
|  | 1 | Introduction and familiarization with Asana
|  | 1 | Plan the roadmap
|  | 1 | Meet with the sponsor
|  | 4.75 | TOTAL TIME
Issues

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
YES | 0.25 | 0.25 | Submit a photo and resume
Yes | 0 | 1.5 | Discuss requirements and feedback from sponsor meeting
yes | 1.25 | 1 | Introduction and familiarization with Asana
Yes | 1.25 | 1 | Plan the roadmap
Yes | 0.75 | 1 | Meet with the sponsor
| 3.5 | 4.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Think of product system requirements questions for Paul
|  | 1 | Review the documents sent from Paul for current biz practices
|  | 2 | Continue conceptualizing requirements and the app. Domain
|  | 1 | Meet with sponsor
|  | 1 | Discuss feedback and recap sponsor meeting
|  | 6.75 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.25 | 0.25 | Obtain username and password for team SE account
Yes | 0.5 | 0.5 | Think of product system requirements questions for Paul
Yes | 1.25 | 1 | Review the documents sent from Paul for current biz practices
Yes | 2 | 2 | Continue conceptualizing requirements and the app. Domain
Yes | 1 | 1 | Meet with sponsor
Yes | 1 | 1 | Discuss feedback and recap sponsor meeting
Yes | 0.75 | 0.75 | Install and familiarize with Node-webkit
| 6.75 | 6.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Review the attendance card sent from Paul
|  | 0.75 | Add risk planning and identify risks in Asana
|  | 1.25 | Continue refining product backlog
|  | 1 | Meet with sponsor
|  | 1 | Recap sponsor meeting
|  | 5.25 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.75 | 1.25 | Review the attendance card sent from Paul
Yes | 1 | 0.75 | Add risk planning and identify risks in Asana
Yes | 1.25 | 1.25 | Continue refining product backlog
Yes | 1 | 1 | Meet with sponsor
Yes | 1 | 1 | Recap sponsor meeting
| 5 | 5.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Create low fidelity prototypes and flowcharts
|  | 1 | Continue product backlog and requirement development
|  | 1 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 5 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
No | 0 | 2 | Create low fidelity prototypes and flowcharts
No | 0 | 1 | Continue product backlog and requirement development
No | 0 | 1 | Meet with the sponsor
No | 0 | 1 | Recap sponsor meeting
| 0 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Create low fidelity prototypes and flowcharts
|  | 1 | Continue product backlog and requirement development
|  | 1 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 1 | Research useful metrics and decide on some
|  | 1 | Discussion of the architecture
|  | 7 | TOTAL TIME
Issues
Did not meet with team and sponsor due to 4th of July

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Create low fidelity prototypes and flowcharts
Yes | 1.5 | 1 | Continue product backlog and requirement development
Yes | 1 | 1 | Meet with the sponsor
Yes | 1 | 1 | Recap sponsor meeting
Yes | 0.5 | 1 | Discussion of the architecture
Yes | 1 |  | Further talk about the requirements of workshops and classes
| 7 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Think about the pros and cons for different check-in methods
|  | 2 | Update the wireframes according to sponsor feedback
|  | 1 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 4.5 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.5 | 0.5 | Think about the pros and cons for different check-in methods
Yes | 2 | 2 | Update the wireframes according to sponsor feedback
Yes | 1 | 1 | Meet with the sponsor
Yes | 1 | 1 | Recap sponsor meeting
Yes | 1 | 0.5 | Create agenda for team meeting
| 5.5 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Do initial assessment of ramaining user stores
|  | 0.5 | Collect and highlight what has been done to this point
|  | 0.5 | Update check-in wireframe
|  | 0.75 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 3.75 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
No | 0 | 1 | Do initial assessment of ramaining user stores
Yes | 0.5 | 0.5 | Collect and highlight what has been done to this point
Yes | 1 | 0.5 | Update check-in wireframe
Yes | 0.75 | 0.75 | Meet with the sponsor
Yes | 1 | 1 | Recap sponsor meeting
Yes | 0.75 |  | Begin coding
| 4 | 3.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Do object modeling diagrams and associations
|  | 1 | Prioritize the product backlog
|  | 1 | Continue coding
|  | 0.45 | Meet with the sponsor
|  | 0.5 | Recap sponsor meeting
|  | 4.95 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.75 | 2 | Do object modeling diagrams and associations
Yes | 0.5 | 1 | Prioritize the product backlog
Yes | 1 | 1 | Continue coding
Yes | 0.45 | 0.45 | Meet with the sponsor
Yes | 0.5 | 0.5 | Recap sponsor meeting
| 4.2 | 4.95 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2.5 | Begin preparing for the presentation and do the powerpoint
|  | 0.5 | Do a dry run of the presentation with the sponsor
|  | 0.5 | Do the presentation
|  | 1 | Code the project
|  | 2 | Start researching and practicing with NodeJS server, Express, and MongoDB
|  | 6.5 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Yes | 2.5 | 2.5 | Begin preparing for the presentation and do the powerpoint
Yes | 0.5 | 0.5 | Do a dry run of the presentation with the sponsor
|  | 0.5 | Do the presentation
|  | 1 | Code the project
Yes | 2 | 2 | Start researching and practicing with NodeJS server, Express, and MongoDB
Yes | 1 | 0.5 | Create agenda for team meeting
| 6 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.15 | 1.5 | Created model files
Yes | 2.15 | 1.15 | Meeting with sponsor and post meeting follow up
No | 2 | 2 | Worked on models for the payment subsystem
| 5.3 | 4.65 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Team meeting on Monday
|  | 2 | Sponsor meeting on Thursday
|  | 3.25 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.25 | 1.25 | Team meeting on Monday
Yes | 2 | 2 | Sponsor meeting on Thursday
| 3.25 | 3.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Continued work on payment models
|  | 1.25 | Team meeting on Monday
|  | 2 | Sponsor meeting on Thursday
|  | 6.25 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
No | 1 | 3 | Continued work on payment models
Yes | 1.25 | 1.25 | Team meeting on Monday
Yes | 2 | 2 | Sponsor meeting on Thursday
| 4.25 | 6.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Fixing JSHint Errors
|  | 1.25 | Team Meeting Monday
|  | 2 | Sponsor Meeting Thursday
|  | 5.25 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Yes | 3 | 2 | Fixing JSHint Errors
Yes | 1.25 | 1.25 | Team Meeting Monday
Yes | 2 | 2 | Sponsor Meeting Thursday
Yes | 2 | 2 | Introduction to Mocha Testing
| 8.25 | 7.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Students Controller Mocha testing
|  | 1.25 | Team meeting Monday
|  | 2 | Sponsor meeting Thursday
|  | 2 | Plan out other controller tests
|  | 8.25 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
No | 4 | 3 | Students Controller Mocha testing
Yes | 1.25 | 1.25 | Team meeting Monday
Yes | 2 | 2 | Sponsor meeting Thursday
Yes | 3 | 2 | Plan out other controller tests
| 10.25 | 8.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | More controller tests
|  | 2 | Finish students controller test
|  | 1.25 | Team meeting Monday
|  | 2 | Sponsor meething Thursday
|  | 10 | Refactoring Program creation to use wizard
|  | 20.25 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Yes | 4 | 5 | More controller tests
Yes | 3 | 2 | Finish students controller test
Yes | 1.5 | 1.25 | Team meeting Monday
Yes | 2 | 2 | Sponsor meething Thursday
No | 0 | 10 | Refactoring Program creation to use wizard
| 10.5 | 20.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Team meeting Monday
|  | 2 | Sponsor meeting Thursday
|  | 3 | Finish Controller Tests
|  | 1 | Create test feature stories
|  | 1 | Calculate Metrics
|  | 8.25 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.5 | 1.25 | Team meeting Monday
Yes | 2 | 2 | Sponsor meeting Thursday
Yes | 5 | 3 | Finish Controller Tests
Yes | 1 | 1 | Create test feature stories
Yes | 1 | 1 | Calculate Metrics
| 10.5 | 8.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Team meeting Monday
|  | 2 | Sponsor meeting Thursday
|  | 2 | Resarch karma for end to end testing
|  | 5.25 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Yes | 1 | 1.25 | Team meeting Monday
Yes | 2 | 2 | Sponsor meeting Thursday
Yes | 3 | 2 | Resarch karma for end to end testing
| 6 | 5.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Team meeting Monday
|  | 2 | Sponsor meeting Thursday
|  | 2 | Test scenarios for end to end testing
|  | 2 | Getting Karma to work
|  | 7.25 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.25 | 1.25 | Team meeting Monday
Yes | 2 | 2 | Sponsor meeting Thursday
Yes | 1.5 | 2 | Test scenarios for end to end testing
No | 2 | 2 | Getting Karma to work
| 6.75 | 7.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Team Meeting Monday
|  | 2 | Sponsor Meeting Thursday
|  | 3 | Learn more about ProtractorJS
|  | 6.25 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.25 | 1.25 | Team Meeting Monday
Yes | 2 | 2 | Sponsor Meeting Thursday
Yes | 3 | 3 | Learn more about ProtractorJS
| 6.25 | 6.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Team Meeting Monday
|  | 2 | Sponsor Meeting Thursday
|  | 4 | Find out how to deal with ng-grid in Protractor
|  | 1 | Project Poster Section
|  | 8.25 | TOTAL TIME
Issues

## 2-Wk11
Second Term - Week 11
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.25 | 1.25 | Team Meeting Monday
Yes | 2 | 2 | Sponsor Meeting Thursday
No | 3 | 4 | Find out how to deal with ng-grid in Protractor
Yes | 0.75 | 1 | Project Poster Section
| 7 | 8.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Team Meeting Monday
|  | 2 | Sponsor Meeting Thursday
|  | 3 | Work around for ng-grid in Protractor
|  | 2 | Finalizing Poster Work
|  | 8.25 | TOTAL TIME
Issues

## 2-Wk12
Second Term - Week 12
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 1.25 | Team Meeting Monday
Yes | 3 | 2 | Sponsor Meeting Thursday
Yes | 3 | 3 | Work around for ng-grid in Protractor
Yes | 1 | 2 | Finalizing Poster Work
| 9 | 8.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sponsor meeting Monday
|  | 3 | Testing registration
|  | 2 | Work on presentation slides
|  | 7 | TOTAL TIME
Issues

## 2-Wk13
Second Term - Week 13
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Sponsor meeting Monday
No | 3 | 3 | Testing registration
Yes | 2 | 2 | Work on presentation slides
| 7 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Dry run presentation
|  | 3 | Finalize testing
|  | 2 | Final Presentation
|  | 7 | TOTAL TIME
Issues

## 2-Wk14
Second Term - Week 14
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Dry run presentation
Yes | 3 | 3 | Finalize testing
Yes | 2 | 2 | Final Presentation
| 7 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Reflection
|  | 2 | Team Reflection Meeting
|  | 4 | TOTAL TIME
Issues

## 2-Wk15
Second Term - Week 15
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Team Reflection
Yes | 2 | 2 | Team Reflection Meeting
| 4 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Technical Report
|  | 1 | Finalize deliverables
|  | 4 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Yes | 3 | 3 | Technical Report
Yes | 1 | 1 | Finalize deliverables
| 4 | 4 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
3.25 | 4.75 | 3.5 | 6.5 | 6.75 | 5.25 | 5 | 5 | 0 | 6 | 7 | 5 | 5.5 | 3.75 | 4 | 4.95 | 4.2 | 7 | 6 | 0 | 0
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-11e | t2-11a | t2-12e | t2-12a | t2-13e | t2-13a | t2-14e | t2-14a | t2-15e | t2-15a | t2-fe | t2-fa
4.65 | 5.3 | 3.25 | 3.25 | 6.25 | 4.25 | 7.25 | 8.25 | 8.25 | 10.25 | 20.25 | 10.5 | 8.25 | 10.5 | 5.25 | 6 | 7.25 | 6.75 | 6.25 | 6.25 | 8.25 | 7 | 8.25 | 9 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 4