## Instructions
Your Name: | Nick
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Yes | 0.5 |  | Attended first class
Yes | 0.5 |  | Discussed expectations of team and team introductions
Yes | 1 |  | Went over the project at a high level
Yes | 1 |  | Met with the project sponsor
| 1 |  | Worked on synopsis
| 4 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Submit a photo and resume
|  | 0.25 | Submit the project synopsis to Dr Ludi
|  | 1 | Introduction and familiarization with Asana
|  | 1 | Plan the roadmap
|  | 1 | Meet with the sponsor
|  | 1.5 | Discuss requirements and feedback from sponsor meeting
|  | 5 | TOTAL TIME
Issues

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
YES | 0.25 | 0.25 | Submit a photo and resume
No | 0 | 0.25 | Submit the project synopsis to Dr Ludi
yes | 1.25 | 1 | Introduction and familiarization with Asana
Yes | 1.25 | 1 | Plan the roadmap
Yes | 0.75 | 1 | Meet with the sponsor
Yes | 1.25 | 1.5 | Discuss requirements and feedback from sponsor meeting
| 4.75 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Submit the project synopsis to Dr Ludi
|  | 0.5 | Think of product system requirements questions for Paul
|  | 1 | Review the documents sent from Paul for current biz practices
|  | 2 | Continue conceptualizing requirements and the app. Domain
|  | 1 | Meet with sponsor
|  | 1 | Discuss feedback and recap sponsor meeting
|  | 0.25 | Plan next agenda
|  | 0.25 | Submit meeting minutes
|  | 6.75 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.25 | 0.25 | Submit the project synopsis to Dr Ludi
Yes | 0.5 | 0.5 | Think of product system requirements questions for Paul
Yes | 1.25 | 1 | Review the documents sent from Paul for current biz practices
Yes | 2 | 2 | Continue conceptualizing requirements and the app. Domain
Yes | 1 | 1 | Meet with sponsor
Yes | 1 | 1 | Discuss feedback and recap sponsor meeting
No | 0 | 0.25 | Plan next agenda
Yes | 0.25 | 0.25 | Submit meeting minutes
Yes | 0.75 | 0.75 | Install and familiarize with Node-webkit
| 7 | 6.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Review the attendance card sent from Paul
|  | 0.75 | Add risk planning and identify risks in Asana
|  | 1.25 | Continue refining product backlog
|  | 1 | Meet with sponsor
|  | 1 | Recap sponsor meeting
|  | 1.5 | Research on project technologies
|  | 6.75 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.75 | 1.25 | Review the attendance card sent from Paul
Yes | 1 | 0.75 | Add risk planning and identify risks in Asana
Yes | 1.25 | 1.25 | Continue refining product backlog
Yes | 1 | 1 | Meet with sponsor
Yes | 1 | 1 | Recap sponsor meeting
| 1 | 1.5 | Research on project technologies
| 6 | 6.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Create low fidelity prototypes and flowcharts
|  | 1 | Continue product backlog and requirement development
|  | 1 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 5 | TOTAL TIME
Issues
It has been decided that Alex will become website coordinator and I will take over as meeting scribe

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
No | 0 | 2 | Create low fidelity prototypes and flowcharts
No | 0 | 1 | Continue product backlog and requirement development
No | 0 | 1 | Meet with the sponsor
No | 0 | 1 | Recap sponsor meeting
| 0 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Create low fidelity prototypes and flowcharts
|  | 1 | Continue product backlog and requirement development
|  | 1 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 1 | Research useful metrics and decide on some
|  | 1 | Discussion of the architecture
|  | 7 | TOTAL TIME
Issues
Did not meet with team and sponsor due to 4th of July

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2 | Create low fidelity prototypes and flowcharts
Yes | 1.5 | 1 | Continue product backlog and requirement development
Yes | 1 | 1 | Meet with the sponsor
Yes | 1 | 1 | Recap sponsor meeting
Yes | 0.75 | 1 | Research useful metrics and decide on some
Yes | 0.5 | 1 | Discussion of the architecture
Yes | 1 |  | Further talk about the requirements of workshops and classes
| 7.75 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Think about the pros and cons for different check-in methods
|  | 2 | Update the wireframes according to sponsor feedback
|  | 1 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 4.5 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.5 | 0.5 | Think about the pros and cons for different check-in methods
Yes | 2 | 2 | Update the wireframes according to sponsor feedback
Yes | 1 | 1 | Meet with the sponsor
Yes | 1 | 1 | Recap sponsor meeting
| 4.5 | 4.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Update the attendance wireframe
|  | 1 | Do initial assessment of ramaining user stores
|  | 0.5 | Collect and highlight what has been done to this point
|  | 0.5 | Update check-in wireframe
|  | 0.75 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 0.5 | Begin coding
|  | 4.75 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.5 | 0.5 | Update the attendance wireframe
No | 0 | 1 | Do initial assessment of ramaining user stores
Yes | 0.5 | 0.5 | Collect and highlight what has been done to this point
Yes | 1 | 0.5 | Update check-in wireframe
Yes | 0.75 | 0.75 | Meet with the sponsor
Yes | 1 | 1 | Recap sponsor meeting
Yes | 0.75 | 0.5 | Begin coding
| 4.5 | 4.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Do object modeling diagrams and associations
|  | 1 | Prioritize the product backlog
|  | 1 | Continue coding
|  | 0.45 | Meet with the sponsor
|  | 0.5 | Recap sponsor meeting
|  | 4.95 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.75 | 2 | Do object modeling diagrams and associations
Yes | 0.5 | 1 | Prioritize the product backlog
Yes | 1 | 1 | Continue coding
Yes | 0.45 | 0.45 | Meet with the sponsor
Yes | 0.5 | 0.5 | Recap sponsor meeting
| 4.2 | 4.95 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2.5 | Begin preparing for the presentation and do the powerpoint
|  | 0.5 | Do a dry run of the presentation with the sponsor
|  | 0.5 | Do the presentation
|  | 1 | Code the project
|  | 2 | Start researching and practicing with NodeJS server, Express, and MongoDB
|  | 6.5 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2.5 | Begin preparing for the presentation and do the powerpoint
Yes | 0.5 | 0.5 | Do a dry run of the presentation with the sponsor
|  | 0.5 | Do the presentation
|  | 1 | Code the project
Yes | 2 | 2 | Start researching and practicing with NodeJS server, Express, and MongoDB
| 4.5 | 6.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
YES | 2 | 2.5 | Begin preparing for the presentation and do the powerpoint
YES | 0.75 | 0.5 | Do a dry run of the presentation with the sponsor
YES | 0.5 | 0.5 | Do the presentation
YES | 2 | 1 | Code the project
YES | 2 | 2 | Start researching and practicing with NodeJS server, Express, and MongoDB
NO | 2 | 2 | Team meeting introduction to technologies
| 9.25 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Sponsor meeting
|  | 1 | Sponsor meeting follow-up
|  | 3 | Start client-side development
|  | 2 | Team meeting to continue discussing technologies and architecture
|  | 6.5 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
YES | 0.5 | 0.5 | Sponsor meeting
YES | 1 | 1 | Sponsor meeting follow-up
NO | 4 | 3 | Start client-side development
| 5.5 | 4.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Client-side development on Programs/Ranks/Classes
|  | 2 | Sponsor meeting and follow-up
|  | 7 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
NO | 6.75 | 5 | Client-side development on Programs/Ranks/Classes
YES | 2 | 2 | Sponsor meeting and follow-up
| 8.75 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Client-side development on Programs/ranks/classes
|  | 2 | Sponsor meeting and follow-up
|  | 1.25 | Team meeting
|  | 5.25 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
NO | 1.75 | 2 | Client-side development on Programs/ranks/classes
YES | 2.25 | 2 | Sponsor meeting and follow-up
YES | 1.5 | 1.25 | Team meeting
| 5.5 | 5.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sponsor meeting and follow-up
|  | 1.5 | Team meeting and technical discussion
|  | 3 | Client-side development on rank/class pages
|  | 2 | Conclude client-side work on Programs
|  | 8.5 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
YES | 2 | 2 | Sponsor meeting and follow-up
YES | 2 | 1.5 | Team meeting and technical discussion
NO | 6.5 | 3 | Client-side development on rank/class pages
YES | 2 | 2 | Conclude client-side work on Programs
| 12.5 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sponsor meeting and follow-up
|  | 1.5 | Team meeting and technical discussion
|  | 8 | Conclude work on client-side CRUD Ranks/Classes
|  | 11.5 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
YES |  | 2 | Sponsor meeting and follow-up
YES |  | 1.5 | Team meeting and technical discussion
NO |  | 8 | Conclude work on client-side CRUD Ranks/Classes
| 0 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sponsor meeting and follow-up
|  | 1.5 | Team meeting and technical discussion
|  | 3 | Implement rank colors
|  | 6.5 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
YES | 2 | 2 | Sponsor meeting and follow-up
YES | 1.5 | 1.5 | Team meeting and technical discussion
YES | 3.5 | 3 | Implement rank colors
YES | 1.25 |  | Client-side improvements to Programs/Classes/Ranks
| 8.25 | 6.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Client-side development for workshops
|  | 2 | Sponsor meeting and follow-up
|  | 1.5 | Team meeting and project planning
|  | 2 | Client-side development for Generate Email Distribution List
|  | 9.5 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
NO | 3 | 4 | Client-side development for workshops
YES | 2 | 2 | Sponsor meeting and follow-up
YES | 1.5 | 1.5 | Team meeting and project planning
YES | 3.5 | 2 | Client-side development for Generate Email Distribution List
NO | 7 |  | Improvements to sub-ranks
| 17 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sponsor meeting and follow-up
|  | 1.5 | Team meeting and project planning
|  | 1 | Improvements to Programs tab UI
|  | 4 | Integrate ranks with achievements
|  | 8.5 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
YES | 2 | 2 | Sponsor meeting and follow-up
YES | 1.5 | 1.5 | Team meeting and project planning
YES | 2 | 1 | Improvements to Programs tab UI
YES | 4 | 4 | Integrate ranks with achievements
YES | 2 | 1 | Bug fixes
NO | 1.25 |  | Improvements to attendance grid
| 12.75 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sponsor meeting and follow-up
|  | 1.5 | Team meeting and project planning
|  | 5 | Development on Attendance tab
|  | 1.5 | Fix Sponsor identified issues
|  | 10 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
YES | 2 | 2 | Sponsor meeting and follow-up
YES | 1.5 | 1.5 | Team meeting and project planning
NO | 7 | 5 | Development on Attendance tab
YES | 2.5 | 1.5 | Fix Sponsor identified issues
YES | 3.5 |  | Misc fixes and style improvements
| 16.5 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sponsor meeting and follow-up
|  | 1.5 | Team meeting and project planning
|  | 4 | Development for achievements
|  | 1 | Development for generating workshop attendee e-mail distribution list
|  | 3 | Development or Attendance tab
|  | 11.5 | TOTAL TIME
Issues

## 2-Wk11
Second Term - Week 11
Accomplished this week
Done? | ACT | EST | Task
YES | 2 | 2 | Sponsor meeting and follow-up
YES | 1.5 | 1.5 | Team meeting and project planning
YES | 4 | 4 | Development for achievements
YES | 1 | 1 | Development for generating workshop attendee e-mail distribution list
YES | 2.25 | 3 | Development or Attendance tab
YES | 0.5 |  | Misc style improvements
| 11.25 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Development for attendance report generation
|  | 2 | Sponsor meeting and follow-up
|  | 1.5 | Team meeting and project planning
|  | 3 | Testing and fixes
|  | 10.5 | TOTAL TIME
Issues

## 2-Wk12
Second Term - Week 12
Accomplished this week
Done? | ACT | EST | Task
YES | 4 | 4 | Development for attendance report generation
YES | 2 | 2 | Sponsor meeting and follow-up
YES | 1.5 | 1.5 | Team meeting and project planning
YES | 3.75 | 3 | Testing and fixes
| 11.25 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Work on poster planning
|  | 1.5 | Team meeting and project planning
|  | 4 | Client development for report generation
|  | 3 | Testing and fixes
|  | 2 | Sponsor meeting and follow up
|  | 11.5 | TOTAL TIME
Issues

## 2-Wk13
Second Term - Week 13
Accomplished this week
Done? | ACT | EST | Task
YES | 1 | 1 | Work on poster planning
YES | 2 | 1.5 | Team meeting and project planning
NO | 2 | 4 | Client development for report generation
NO | 1.25 | 3 | Testing and fixes
YES | 2 |  | Add sort by last checkin time
YES | 1.5 | 2 | Sponsor Meeting and follow up
| 9.75 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Testing and fixes
|  | 1.5 | Team meeting and poster planning
|  | 2 | Poster presentation
|  | 2 | Sponsor meeting and follow-up
|  | 2 | Work on demo videos
|  | 11.5 | TOTAL TIME
Issues

## 2-Wk14
Second Term - Week 14
Accomplished this week
Done? | ACT | EST | Task
NO | 8.5 | 4 | Testing and fixes
YES | 1.75 | 1.5 | Team meeting and poster planning
YES | 2 | 2 | Poster presentation
YES | 1 | 2 | Sponsor meeting and follow-up
NO | 1.75 | 2 | Work on demo videos
| 15 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Testing and fixes
|  | 2 | Sponsor meeting and follow-up
|  | 1.5 | Work on demo videos
|  | 8.5 | TOTAL TIME
Issues

## 2-Wk15
Second Term - Week 15
Accomplished this week
Done? | ACT | EST | Task
NO | 4.75 | 5 | Testing and fixes
YES | 1.5 | 2 | Sponsor meeting and follow-up
NO | 1.5 | 1.5 | Work on demo videos
| 7.75 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sponsor meeting and follow-up
|  | 4 | Testing and fixes
|  | 2 | Work on demo videos
|  | 1.5 | Team meeting and follow-up
|  | 7 | Work on tutorial video
|  | 16.5 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Sponsor meeting and follow-up
| 2 | 4 | Testing and fixes
| 3 | 2 | Work on demo videos
| 1.5 | 1.5 | Team meeting and follow-up
| 8 | 7 | Work on tutorial video
| 1.5 |  | Client-side enhancements
| 2 |  | Work on technical report
| 20 | 16.5 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
4 | 5 | 4.75 | 6.25 | 7 | 6.75 | 6 | 5 | 0 | 7 | 7.75 | 4.5 | 4.5 | 4.75 | 4.5 | 4.95 | 4.2 | 6.5 | 4.5 | 0 | 0
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-11e | t2-11a | t2-12e | t2-12a | t2-13e | t2-13a | t2-14e | t2-14a | t2-15e | t2-15a | t2-fe | t2-fa
8.5 | 9.25 | 4.5 | 5.5 | 7 | 8.75 | 5.25 | 5.5 | 8.5 | 12.5 | 11.5 | 0 | 6.5 | 8.25 | 9.5 | 17 | 9.5 | 12.75 | 10 | 16.5 | 11.5 | 11.25 | 10.5 | 11.25 | 11.5 | 9.75 | 11.5 | 15 | 8.5 | 7.75 | 16.5 | 20